## Slide 1: CHAPTER 12
PROJECT CASH FLOW

## Slide 2
제1장 History and Basic Concepts
제2장 Preparing the Bid Package
제3장 Issues During Construction
제4장 Contracts
제5장 Legal Structure
제6장 Impact of Taxes
제7장 Project Planning
제8장 Project Scheduling
제9장 Scheduling: Program Evaluation and Review Technique Networks and Linear Operations
제10장 Resource-Related and Advanced Linear Scheduling Techniques
제11장 The Mathematics of Money
제12장 Project Cash Flow
제13장 Project Funding
제14장 Equipment Ownership
제15장 Equipment Productivity
제16장 Construction Labor
제17장 Estimating Process
제18장 Cost Control
제19장 Materials Management
제20장 Safety

## Slide 3: 12.1 Cash Flow Projection (1/2)
The projection of income and expense during the life of a project can be developed from several time-scheduling aids used by the contractor. 스케줄링 도구를 이용하여 프로젝트 기간 내 발생하는 수입과 비용 추산 가능
The owner requires the contractor to provide an S-curve of estimated progress and costs across the life of the project. 발주자는 시공사에 시간 축과 준공률 축을 갖는 S-Curve (Production curve, Objective chart) 제공을 요구
The contractor develops this by constructing a simple bar chart of the project, assigning costs to the bars, and smoothly connecting the projected amounts of expenditures over time. 시공사는 공정별로 바차트에 비용을 할당한 후 이를 스무딩(Smoothing)하여 S-Curve를 작성

## Slide 4: 12.1 Cash Flow Projection (2/2)
FIGURE 12.1 Development of the S-curve

## Slide 5: 12.2 Cash Flow to the Contractor (1/2)
FIGURE 12.2 Expenses and payments profiles
Pay = 1.25(indirect expense + direct expense) − 0.10[1.25(indirect expense + direct expense)]
= 1.125(indirect expense + direct expense)
Profit or markup: 25%
Retainage: 10% 지불유예금: 공정이 50%를 넘어서면 부과하지 않음
30일 지연 지급
1.2530 – 0.12530
= 1.125  30 = 33.75
1.125  100
1.25  180 – 12.5(Retainage)
Total Expense : $200,000
Total Bid Price : $250,000
비용
수입
자금 부족
1.25  200
누적 Retainage = 125 – 112.5 = 12.5

## Slide 6: 12.2 Cash Flow to the Contractor (2/2)
FIGURE 12.3 Influence of front (or mobilization) payment on profiles
자금 부족 완화  금융 비용 절감
The prime rate is the interest rate charged preferred customers who are rated as reliable and who represent an extremely small risk of default. 기본 이율: 최소의 위험을 가진 고객에 대한 이자율
Construction Contractor = Prime Rate + Customer Risk. 대출 이율 = 기본 이율 + 위험 할증
선수금, 착수금 지급: 시공자에 대한 신뢰가 있는 경우 금융비용 절감을 위해 발주자가 지급  금융비용 절감으로 인해 원가절감 효과 발생
선수금, 착수금
동원지불
자금
부족
대금지급을 3개월 앞당김

## Slide 7: 12.3 Overdraft Requirements (1/3)
2월중
기간
시점
2월말
3월초
3월중
기간
비용
이자
수입
조달금리 : 1%/월
+
+
-
+
-
+
-
+
-
101,303 – 33,750 + 80,000  147,553 + 1,476 = 149,029
2월 잔고 – 3월 수입 + 3월 비용  3월 부족 자금 + 이자 = 3월 잔고
2월 대출 필요 잔고
(필요 신용)
3월 대출 필요 잔고
(필요 신용)
최대 신용 규모
시점
3월말
4월초
4월중
기간
시점
4월말
5월초
5월중
기간
시점
5월말
6월초
6월중
기간
대출 필요 잔고
250,000 - 200,000  50,000 - (300 + 1,003 + 1,476 + 903) = 46,318
실질 수익 =
수익 - 금융비용

## Slide 8: 12.3 Overdraft Requirements (2/3)
FIGURE 12.4 Plot of maximum overdraft
$250K : Total Billed
$180K : Direct Cost
$200K : Total Cost
1월말
2월초
2월말
3월초
3월말
4월초
4월말
5월초
5월말
6월초
6월말
7월초
0월말
1월초
수입
실질 수익 = 수익(=수입 – 지출) – 금융비용
250,000 – 200,000  50,000
50,000 – (300 + 1,003 + 1,476 + 903) = 46,318
자금 부족

## Slide 9: 12.3 Overdraft Requirements (3/3)
FIGURE 12.5 Composite overdraft profiles
부족 자금

## Slide 10: 12.4 Comparison of Payment Schemes (1/4)
FIGURE 12.6 ROR for small bar chart problem
비용 + 이자
수익
The IRR for a given sequence of payments and expenditures
수익률은 수익의 현재가치와 비용의 현재가치의 합을 0으로 만들어 주는 이자율

## Slide 11: 12.4 Comparison of Payment Schemes (2/4)
20%
25%
22%
보간법 이용

## Slide 12: 12.4 Comparison of Payment Schemes (3/4)
FIGURE 12.7 ROR for small bar chart problem with mobilization payment : 동원 지불 $20,000
최대 신용 규모
$37,500  $17,500
$0  $17,500



## Slide 13: 12.4 Comparison of Payment Schemes (4/4)
30%
32%
34%
수익률 증가
20.45%  32.62%